## Sheet1
t
| Project start date | Project name |  | Students Names |  |  | Project coordinator | Project firm | March | [26 empty] | April | [29 empty] | May
| 2024-03-09 | 5g Handover using ML |  | Dobosan Robert-Gabriel, Preda Bogdan |  |  | Cornel Balint | Lasting Software | time axis 2024-03-09 to 2024-05-24
# | ACTIVITY | Assigned To | Start | End | Days | Status | %Done
1 | Project kick-off | All | 2024-03-09 | 2024-05-19 | 68 | Complete | 100%
2 | Conduct research on 5G technology | All | 2024-03-09 | 2024-03-19 | 10 | Complete | 100% | bar: 2024-03-09 to 2024-03-19
3 | Study handover procedures in 5G | All | 2024-03-20 | 2024-03-25 | 5 | Complete | 100% | bar: 2024-03-20 to 2024-03-25
4 | Investigate parameters influencing handover | All | 2024-03-26 | 2024-04-03 | 7 | Complete | 100% | bar: 2024-03-26 to 2024-04-03
5 | Define project objectives and goals | All | 2024-04-04 | 2024-04-12 | 8 | Complete | 100% | bar: 2024-04-04 to 2024-04-12
6 | Develop plan for applying machine learning | All | 2024-04-12 | 2024-04-20 | 7 | Complete | 100% | bar: 2024-04-13 to 2024-04-20
7 | Design architecture for the machine learning model | All | 2024-04-21 | 2024-04-28 | 7 | Complete | 100% | bar: 2024-04-21 to 2024-04-28
8 | Gather and preprocess data | All | 2024-04-29 | 2024-05-06 | 7 | Complete | 100% | bar: 2024-04-29 to 2024-05-06
9 | Implement machine learning model and training | All | 2024-05-07 | 2024-05-11 | 4 | Complete | 100% | bar: 2024-05-06 to 2024-05-12
10 | Implement a graphic web aplication for demonstration | All | 2024-05-08 | 2024-05-12 | 4 | Complete | 100% | bar: 2024-05-06 to 2024-05-12
11 | Test and validate machine learning model | All | 2024-05-12 | 2024-05-13 | 1 | Complete | 100% | bar: 2024-05-12 to 2024-05-15
12 | Evaluate model performance and iterate | All | 2024-05-14 | 2024-05-15 | 1 | Complete | 100% | bar: 2024-05-14 to 2024-05-15
13 | Prepare project documentation and final report | All | 2024-05-16 | 2024-05-17 | 1 | Complete | 100% | bar: 2024-05-16 to 2024-05-17
14 | Final Documentation review | All | 2024-05-17 | 2024-05-19 | 2 | Complete | 100% | bar: 2024-05-18 to 2024-05-20
15 | Project Presentation | All | //2024 | //2024 | ? | Complete | 100%
[8 empty] | Legend: | 2024-03-09: Not started; 2024-03-11: In progress; 2024-03-13: Complete